## Sheet1
Unique ID | Entity/Model | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Project | As a partner I want to submit a description of a task/project so that it will be checked by an admin to be posted. | 2 | Nihal Rashed
1.1 |  | As a user I want to view project's information. | 1
1.2 |  | Project's information can be updated in accordance to the required functionality. | 3
1.3 |  | As a partner/admin I can delete the task/project as long as it’s not posted. | 3
2 | Event | As a member I want to create an event so that members can book a place in it. | 2 | Nada Elaraby
2.1 |  | As a member I want to view an event's description so that I can book a place in it. | 1
2.2 |  | As a member I want to book a place in an event (based on the event’s type). | 3
2.3 |  | As an admin I want to delete an event. | 3
3 | Event Request | As a partner/consultancy agency/admin I want to submit a request to organize an event. | 2 | Abdelrahman Ashraf
3.1 |  | As a partner/consultancy agency/admin I want to edit an event request before it be approved. | 3
3.2 |  | As a partner/consultancy agency/admin I want to view submitted event requests. | 1
3.3 |  | As a partner/consultancy agency/admin I want to delete an event request. | 3
4 | Member | I want to create a profile including my information | 2 | Ahmed Mohamed
4.1 |  | I want to update my profile's information. | 3
4.2 |  | As a user I want to view a member's profile. | 1
4.3 |  | As an admin I want to delete a member's profile. | 3
5 | Consultancy Agency | I want to create a profile including my information | 2 | Omar Khaled
5.1 |  | I want to update my profile's information. | 3
5.2 |  | As a user I want to view an agency's profile. | 1
5.3 |  | As an admin I want to delete an agency's profile. | 3
6 | Partner | I want to create a profile including my information | 2 | Mariam Bakhaty
6.1 |  | I want to update my profile's information. | 3
6.2 |  | As a user I want to view a parneter's profile. | 1
6.3 |  | As an admin I want to delete a partner's profile. | 3
7 | Admin | I want to create an account on the website. | 2 | Ahmed Samhar
7.1 |  | I want to update my account's information. | 3
7.2 |  | As an admin I want to view my account profile. | 1
7.3 |  | As an admin I want to delete my account. | 3
8 | Notification | Notifications should be created to notify users with specefic information. | 2 | Ahmed Alaa
8.1 |  | The read/unread status of the notification should be updated. | 3
8.2 |  | As a user I want to view notifications sent to me. | 1
8.3 |  | As a user I want to delete notifications that I recived. | 3
9 | Orientation Invitation | As an accepted candidate I want to receive a task orientation invitation so that I get to know about the task I am going to work on. | 1 | Karim Elgendy
9.1 |  | As a consultancy agency/admin i want to send a task orientation invitation so that candidates can get a head start of what their task is. | 2
9.2 |  | As a consultancy agency/admin i want to update a task orientation invitation' information. | 3
9.3 |  | As a consultancy agency/admin I want to delete the orientation invitations sent to me. | 3
10 | Application | As an admin/consultancy agency I want to create an application form that the members can fill in order to apply for a task/project. | 2 | Ahmed Hisham
10.1 |  | As an admin/consultancy agency I want to edit an application form that the members can fill in order to apply for a task/project. | 3
10.2 |  | As a member I want to view and fill in the application to apply for a task/project. | 1
10.3 |  | As an admin/consultancy agency I want to delete an application from. | 3