## Sheet1
To be implemented in later sprints
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a partner I want to submit a description of a task/project. | 2 | Mariam Bakhaty | Omar Khaled | Nada Elaraby
1.1 | As a partner I want to assign a consultancy agency to a project. | 1 | Mariam Bakhaty | Omar Khaled | Nada Elaraby
1.2 | As a partner I want to approve/disapprove the final draft of the task/project. | 1 | Mariam Bakhaty | Omar Khaled | Nada Elaraby
1.3 | As a partner I can edit or delete the task/project as long as it’s not posted. | 3 | Ahmed Samhar | Ahmed Mohamed | Mariam Bakhaty
1.4 | As a partner I want to send a task orientation invitation to accepted candidates so that they get to know about the task that they are going to work on. | 2
1.5 | As a partner I want to review the final work of the candidate who is working on my task/project. | 1 | Omar Khaled | Nihal Rashed | Ahmed Hisham
1.6 | As a partner I want to submit a request to organize an event. | 1 | Ahmed Samhar | Ahmed Mohamed | Mariam Bakhaty
1.7 | As a patrner I want to give the attendees a form to rate the event and give a feedback. | 2
2 | As a consultancy agency I want to approve/disapprove the final draft of the task/project so the admin can post it. | 1 | Ahmed Samhar | Ahmed Mohamed | Mariam Bakhaty
2.1 | As a conultancy agency I want to apply for tasks/projects. | 2 | Ahmed Hisham | Karim Elgendy | Ahmed Alaa
2.2 | As a consultancy agency I want to assign one of the candidates who applied for the task/project. | 3 | Abdelrahman Ashraf | Nada Elaraby | Ahmed Alaa
2.3 | As a consultancy agency I want to review the final work of the candidate who is working on my task/project. | 1 | Ahmed Mohamed | Nihal Rashed | Nada Elaraby
2.4 | As a consultancy agency I want to request to organize an event. | 1 | Nihal Rashed | Ahmed Mohamed | Ahmed Alaa
2.5 | As a consultancy agency I want to give the attendees a form to rate the event and give a feedback. | 2
3 | As an admin I want to further check the description of a task/project so that it will be posted for candidates to apply. | 1 | Nihal Rashed | Ahmed Mohamed | Ahmed Alaa
3.1 | As an admin I want to identify a task/project with a set of attributes so that it defines it. | 2 | Ahmed Hisham | Karim Elgendy | Ahmed Alaa
3.2 | As an admin I want to send a final draft of the task/project so that the partner can approve posting it. | 1 | Abdelrahman Ashraf | Nada Elaraby | Ahmed Alaa
3.3 | As an admin I want to post the task/project to the website so that candidates can apply for it. | 1 | Abdelrahman Ashraf | Nada Elaraby | Ahmed Alaa
3.4 | As an admin I want to assign one of the candidates who applied for the task/project. | 3 | Ahmed Mohamed | Nihal Rashed | Nada Elaraby
3.5 | As an admin I want to notify accepted candidates that he was accepted for a task/project | 1 | Nihal Rashed | Ahmed Mohamed | Ahmed Alaa
3.6 | As an admin I want to notify rejected candidates that he was rejected for a task/project | low(3)
3.7 | As an admin I want to accept/reject event requests. | 1 | Ahmed Mohamed | Nihal Rashed | Nada Elaraby
3.8 | As an admin I want to create an event | 2 | Karim Elgendy | Ahmed Samhar | Abdelrahman Ashraf
3.9 | As an admin I want to give the attendees a form to rate the event and give a feedback. | 2
4 | As a candidate I want to view tasks so that I can apply for them. | 1 | Karim Elgendy | Ahmed Samhar | Abdelrahman Ashraf
4.1 | As a candidate I want to apply for tasks/projects (if eligible) so that I can be chosen by an admin to work on it. | 3 | Nada Elaraby | Ahmed Mohamed | Abdelrahman Ashraf
4.2 | As an accepted candidate I want to be notified that I was accepted for a task/project. | 1 | Nada Elaraby | Ahmed Mohamed | Abdelrahman Ashraf
4.3 | As a rejected candidate I want to be notified that I was rejected for a task/project so that I start looking for other tasks/projects. | low(3)
4.4 | As an accepted candidate I want to receive a task orientation invitation so that I get to know about the task I am going to work on. | 1
4.5 | As a candidate I need my skills to be matched with the required skills of the projects. | 5 | Ahmed Alaa | Nihal Rashed | Abdelrahman Ashraf
4.6 | As a candidate I want to view recommendations of tasks that matches my set of skills so that I can easily choose a task that suits me. | 2
4.7 | As a candidate I want to view an events so that I can book a place in it. | 1 | Karim Elgendy | Ahmed Samhar | Abdelrahman Ashraf
4.8 | As a candidate I want to book a place in an event (based on the event’s type). | 3 | Omar Khaled | Nihal Rashed | Ahmed Hisham
4.9 | As a candidate I want that the events I attended be added on my profile. | 2 | Nihal Rashed | Ahmed Mohamed | Ahmed Alaa
4.10 | As a candidate I want to rate the event after attending it and send feedback through a promoted form. | 1
4.11 | As a registered user I want to view the cycle of the tasks/projects and their current states. | 1